FASTAPI + OLLAMA + RAG + AI ENGINEERING

Structured Learning Timeline

Start: 5 October 2026  |  Pace: No rush, no skipped fundamentals

Goal: move from understanding RAG internals manually to building production-grade AI applications, then learn LangChain, LlamaIndex, agents, and LangGraph only after the underlying concepts are clear.

# 1. Learning Rules

Do not rush because a framework can hide the underlying concept.

Do not skip a topic until you can explain it and implement a small version yourself.

Each week contains learning, coding practice, debugging, and a checkpoint.

Use the manual implementations as the foundation; frameworks come later.

If a checkpoint fails, repeat that week rather than advancing by date.

Target pace: about 1.5–2 hours/day, 5 days/week. Extra time is optional, not required.

# 2. Current Position — 5 October 2026

Completed:

Python/FastAPI/Ollama basics

Embeddings with nomic-embed-text

Cosine similarity and semantic search

Top-K retrieval

Chunking and chunk overlap

PDF ingestion with pypdf

Manual RAG pipeline

ChromaDB

Persistent vector storage

Metadata: source, page, and chunk

Multi-document ingestion structure

Basic metadata filtering

Current next topic: source citations, followed by retrieval-quality improvements.

# 3. Master Timeline

| Week | Dates | Phase | Topics | Checkpoint |
| --- | --- | --- | --- | --- |
| Week 1 | 5–11 Oct 2026 | RAG citations + retrieval foundations | Source/page citations; reliable metadata-based citations; distance vs similarity; why Top-K alone is insufficient. | Build a cited multi-document RAG query. |
| Week 2 | 12–18 Oct | Chunking strategies | Fixed-size vs sentence/paragraph chunks; overlap trade-offs; chunk size experiments; preserving document structure. | Compare retrieval quality across chunk sizes. |
| Week 3 | 19–25 Oct | Retrieval quality | Similarity/distance thresholds; no-answer behavior; Top-K tuning; retrieval debugging. | RAG refuses confidently when evidence is weak. |
| Week 4 | 26 Oct–1 Nov | Hybrid search | Keyword + semantic retrieval; when embeddings miss exact terms; combining retrieval signals. | Build a basic hybrid retriever. |
| Week 5 | 2–8 Nov | Reranking | Why first-stage retrieval is not enough; rerank retrieved candidates; final context selection. | Build retrieve → rerank → context pipeline. |
| Week 6 | 9–15 Nov | Context engineering | Remove redundant chunks; context limits; ordering; answer grounding; prompt design. | Produce compact, relevant context for the LLM. |
| Week 7 | 16–22 Nov | Advanced multi-document RAG | Document IDs; update/delete; per-document metadata; user/document isolation. | Manage a real document collection. |
| Week 8 | 23–29 Nov | RAG + conversation memory | Chat history; short-term memory; follow-up questions; context vs memory. | Ask follow-up questions without losing context. |
| Week 9 | 30 Nov–6 Dec | FastAPI RAG API | Upload, ingest, ask, list, delete endpoints; request/response models. | Expose the RAG system as a clean API. |
| Week 10 | 7–13 Dec | Production API foundations | Async/background work; streaming; validation; error handling; logging. | Build a reliable RAG backend. |
| Week 11 | 14–20 Dec | RAG application architecture | Frontend/API/vector DB/LLM separation; configuration; environment variables; service boundaries. | Design the complete AI backend architecture. |
| Week 12 | 21–27 Dec | Evaluation | Retrieval evaluation; answer quality; groundedness; test datasets; failure analysis. | Measure RAG instead of judging it only by feel. |
| Week 13 | 28 Dec–3 Jan | Consolidation project | Rebuild the RAG system cleanly from scratch using your own architecture. | End-to-end RAG project checkpoint. |
| Week 14 | 4–10 Jan 2027 | LangChain fundamentals | Map your manual pipeline to LangChain components; loaders, splitters, embeddings, vector stores, retrievers. | Recreate your RAG using LangChain. |
| Week 15 | 11–17 Jan | LangChain advanced RAG | Retrievers, chains, prompts, memory patterns, structured outputs. | Build a maintainable LangChain RAG. |
| Week 16 | 18–24 Jan | LlamaIndex | Indexing, document/query engines, retrieval concepts, comparison with LangChain. | Know when LlamaIndex is useful. |
| Week 17 | 25–31 Jan | Tool/function calling | Structured tool calls; API/database tools; tool schemas; execution loop. | Build an LLM that can call a tool. |
| Week 18 | 1–7 Feb | Agents | Agent loop; planning vs execution; tool selection; failure handling; agent boundaries. | Build a simple useful agent. |
| Week 19 | 8–14 Feb | Agent + RAG | Agent decides when to search; RAG as a tool; source-grounded agent answers. | Build a document-aware agent. |
| Week 20 | 15–21 Feb | LangGraph fundamentals | State, nodes, edges, conditional routing, persistence. | Build a small deterministic AI workflow. |
| Week 21 | 22–28 Feb | LangGraph agent workflows | Retries, validation, human checkpoints, multi-step stateful workflows. | Build a robust agent workflow. |
| Week 22 | 1–7 Mar | Production AI concerns | Security, rate limiting, caching, observability, cost/latency, model selection. | Harden the AI service. |
| Week 23 | 8–14 Mar | Capstone build | Combine FastAPI + RAG + vector DB + Ollama + citations + memory + tools. | Build a portfolio-grade AI application. |
| Week 24 | 15–21 Mar | Finalization | Testing, evaluation, documentation, architecture diagram, deployment plan, demo preparation. | Complete and document the capstone. |

# 4. Phase Milestones

15 November 2026 — Retrieval mastery: You can explain and debug chunking, thresholds, hybrid retrieval, reranking, and context selection.

27 December 2026 — RAG mastery: You can build a complete multi-document RAG system with FastAPI, memory, citations, and evaluation.

31 January 2027 — Framework mastery: You understand LangChain and LlamaIndex because you already understand the underlying RAG components.

28 February 2027 — Agent mastery: You can build tool-using agents and stateful workflows with LangGraph.

21 March 2027 — AI engineering milestone: You have a documented, tested, portfolio-grade AI application.

# 5. Weekly Study Pattern

Day 1 — Learn the concept and understand why it exists.

Day 2 — Implement a small version manually.

Day 3 — Integrate it into the existing RAG project.

Day 4 — Test edge cases and deliberately break/debug it.

Day 5 — Review, explain the concept without notes, and complete the checkpoint.

Weekend — Optional catch-up/project work; do not advance if the checkpoint is not understood.

# 6. What We Will NOT Skip

The following concepts will be understood before their corresponding frameworks are introduced:

Embeddings before vector databases

Similarity search before retrievers

Chunking before advanced document loaders

RAG internals before LangChain

Tool calling before agents

State/workflows before LangGraph

Evaluation before calling a RAG system 'good'

API architecture before production deployment

# 7. Definition of 'Done'

A topic is considered complete only when you can: (1) explain what it does, (2) explain why it is needed, (3) write or modify a small implementation, (4) debug a common failure, and (5) connect it to the larger RAG/AI architecture.

# 8. Final Target Architecture

By the end of this roadmap, the target is not simply 'knowing LangChain'. The goal is to understand and build AI systems end-to-end:

Frontend → FastAPI → ingestion/retrieval → vector database → reranking/context → Ollama/LLM → citations/tools → evaluation → monitoring/deployment

Start date: 5 October 2026  •  Planned completion: 21 March 2027